UNADOPTED.

GLENDALE COMMUNITY COLLEGE DISTRICT

CITIZENS’ BOND OVERSIGHT COMMITTEE

MINUTES

Zoom Teleconference/Live Stream

May 5, 2025

4:30 p.m. – 6:00 p.m.

Present: Tina Parsegian; Monica Campagna; Roberta Hagopian; Harry Leon; Daniel Kim

Resource: Amy Williams, proxy for Sharlene Coleal

Absent: Zanku Armenian;

Guests: Dr. Ryan Cornner; Silva Sorkazian, Patrick Shahnazarian; Cliff Gimbert

- Call to Order

The meeting was called to order at 4:39 pm by Vice Chair, Tina Parsegian.

Recording Secretary confirmed that the meeting notice was posted 72 hours in advance of meeting.

- Introduction of Amy Williams – Associate Vice President, Administrative Services

- Approval of Minutes of February 3, 2025

- Informational Items - None

- Measure GC Progress Report – Silva Sorkazian, Interim Assistant Facilities Director, Bond Projects and Construction

Silva Sorkazian presented the financial status of the college's projects, noting that the top-tier figures for the month of April had not changed. The encumbrance totals had increased significantly with the start of the Camino Real renovation construction project, while unencumbered funds had decreased. The expenditure to date had increased to $304 million, and the program reserves had increased by nearly $3 million. Silva also discussed the status of completed projects and those in construction, including the Buena Vista phase one and two, which are technically complete and occupied. The Camino Real renovation project has encumbered $8.3 million for Horizons construction and has spent $769,000 to date. The program reserves are expected to be available for reallocation to new projects once the reconciliation process is complete. Zanku Armenian inquired about the decision-making process for the $7 million in program reserves, to which Dr. Cornner explained that it is for risk and contingency, and as the project comes closer to being complete, the College can assess the risk more closely and release the money accordingly. Dr. Cornner also mentioned that the final closeout of Buena Vista will relieve a significant risk, and the number of change orders for Camino Real will help assess how much of the contingency will be needed.

#### Financial Status of College Projects:

#### Construction Management and Project Updates

In the meeting, the team discussed the construction management and project management aspects of their ongoing projects. They mentioned the selection of Cordova as the construction manager and the progress of the Camino Real Building renovation project. The team also discussed the potential impact of tariffs on the project and the status of the Adam Schiff funding. They also shared updates on the San Gabriel Second Floor Level 2 Math Department renovations and the Camino Real Building renovation. The team also discussed the demolition event held on the 23rd and the sentiment behind it.

#### Project Updates and Commission Appointments

In the meeting, Silva presented the project updates, which included the completion of the Performing and Fine Arts Center, the installation of solar panels in the parking lot, and the approval of the ECA loan for the solar project. Zanku was appointed to the Glendale Water and Power Commission and requested a change in the meeting schedule to accommodate his new role. The minutes of the previous meeting were approved, and the meeting was adjourned.

### Action:

- Rosa Buford to check committee members' availability and propose alternative meeting dates/times to avoid conflict with Zanku's Glendale Water and Power Commission meetings.

- Silva to forward the PowerPoint presentation to committee members after the meeting.

- Silva/GCC team to post the presentation on the capital improvements web page for public access.

- Patrick Shahnazarian to provide a proposal for installing solar panels at the Garfield campus and potentially on the Verdugo gym roof.

- Patrick to finalize the scope of the solar project within the $3 million ECAA loan limit and submit the application.

- Zanku to assist with communication between GCC and the City of Glendale regarding the solar net metering system.

- Amy Williams to continue working on getting the Adam Schiff funding released, including completing HUD documentation and historical research